## Sheet1
Task | Start Date | Days to complete | 19th July | 20th July | 21st July | 22nd July | 23rd July | 24th July | 25th July | 26th July | 27th July | 28th July | 29th July | 30th July | 31st July | 1st August | 2nd August | 3rd August | 4th August | 5th August | 6th August | 7th August | 8th August | 9th August | 10th August | 11th August | 12th August | 13th August | 14th August | 15th August | 16th August | 17th August | 18th August | 19th August | 20th August | 21st August
Log in interface | 19th July | 3
Question gathering | 22th July | 1
Present Question | 23th July | 3
User making choice | 26th July | 2
Calculating results | 28th July | 2
Finish single player game | 30th July | 2
Build the multiplayer environment | 3rd August | 4
Database creation | 7th August | 4
Self testing | 11th August | 4
External testing | 15th August | 4
Paperwork | 19th August | 32