## Sheet1
ADS Game Project Schedule |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
Task | Start Date | End Date | Days | 17th June | 18th June | 19th June | 20th June | 21st June | 22nd June | 23rd June | 24th June | 25th June | 26th June | 27th June | 28th June | 29th June | 30th June | 1st July | 2nd July | 3rd July | 4th July | 5th July | 6th July | 7th July | 8th July | 9th July | 10th July | 11th July | 12th July | 13th July | 14th July | 15th July | 16th July | 17th July | 18th July | 19th July | 20th July | 21st July | 22nd July | 23rd July | 24th July | 25th July | 26th July | 27th July | 28th July | 29th July | 30th July | 31st July | 1st August | 2nd August | 3rd August | 4th August | 5th August | 6th August | 7th August | 8th August | 9th August | 10th August | 11th August | 12th August | 13th August | 14th August | 15th August | 16th August | 17th August | 18th August | 19th August | 20th August | 21st August | 22nd August | 23rd August | 24th August | 25th August | 26th August | 27th August | 28th August | 29th August | 30th August | 31st August | 1st Sep | 2nd Sep | 3rd Sep | 4th Sep | 5th Sep | 6th Sep
Stage1: Planning
| 19th July |  | 3
| 22th July |  | 1
| 23th July |  | 3
| 26th July |  | 2
| 28th July |  | 2
| 30th July |  | 2
| 3rd August |  | 4 | bar: Week 3 1st July to Week 3 3rd July
| 7th August |  | 4 | bar: Week 3 4th July to Week 3 7th July
| 11th August |  | 4 | bar: Week 4 8th July to Week 4 9th July
| 15th August |  | 4
| 19th August |  | 32
Stage2: Developing
Log in interface | 19th July |  | 3
Question gathering | 22th July |  | 1
Present Question | 23th July |  | 3
User making choice | 26th July |  | 2
Calculating results | 28th July |  | 2
Finish single player game | 30th July |  | 2
Build the multiplayer environment | 3rd August |  | 4
Database creation | 7th August |  | 4
Self testing | 11th August |  | 4
External testing | 15th August |  | 4
Stage3: Evaluating
Stage4: Paperworking